EDIPUS: European Digital Portfolio for University Students (project November 2015 -  October 2017)

Output/ Multiplier events/ Training Activity leaders:

Output 1- ISEP

Output 2 – EAEC

Output 3 - FUEM

Output 4- Enoros Consulting

Output 5- UPRC

E1- EAEC

E2- Enoros Consulting

E3/ E4- ISEP

E5- UNIMED

E6- Eurocrea Merchant

E7/ E8 – University of Vienna

E9-E10 – FUEM

E11-E12- UPRC

E13/E14- ESN

C1- EAEC – planned for M13 in Greece

Two Year Plan Outline

YEAR 1

December 2015: Meeting 1, Cyprus

Clarification of the management, organization and communication plan

Explanation of the activities and the deliverables, including their timeframe

Plan of action by Output Leaders

Discuss the structure and technical specifications of the DPP (O1/A1) and the development of the DPP Tool (O2/A1)

Discuss the survey for the needs of university students, career officers and employers (O1/A2)

Project Image (logo)

Web design structure

Indicators of progress (QA Strategy+ Contingency plan)

Dissemination Plan

Internal Evaluation

June 2016: Meeting 2 Italy

Dissemination leaflets and material for the project and the upcoming 1st Local multiplier events (E1, E3, E5, E7, E9, E11, E13)

Discussion of Output 1 Results

Outputs 2 (A2), O3 (A1), O4 (A1/A2) plan of implementation

Design and development of the Database/Platform (O3/A1)

Testing and technical adjustments of the Database (O2/A2)

Design the structure and gather the material needed for the DP User Guide (O4/A1) and development of the content (O4/A2)

Discussion for the organisation of C1- Training activity in Greece

YEAR 2

November 2016: Meeting 3 Greece

Progress on the testing and technical adjustment of the DPP (O2/A2)

Progress on design and development of the Database/Platform (O3/A1) and discussion for its testing and technical adjustment (O3/A2)

Progress on the development of the content for the Guidebook (O4/A2)

Discussion for translations in all partner languages (O2/A3, O4/A3)

Coordination for the 1st multiplier local events and announcements

Design, structure and pilot testing arrangements for the training course for University students (O5/A1, A2)

Implementation of the C1 Training activity

Internal Evaluation- Begin assessment procedure on the pilot testing phases

April 2017: Meeting 4 Austria

Promotion activities for upcoming events

Dissemination leaflets and material for the project and the upcoming 2nd Local multiplier events (E2, E4, E6, E8, E10, E12, E14)

Launch the Digital Portfolio Portal

Finalisation and presentation of the Digital Portfolio Database

Progress on translation of the content of the DP User Guidebook

Feedback from the pilot testing of the EDIPUS training course

Internal Evaluation- Begin assessment procedure

Final Press conference for results

Internal Evaluation- progress on assessment procedure for the pilot testing phases

September-October 2017: Meeting 5 Cyprus

Closure of any outstanding issues

Internal Evaluation reports

Preparation of Final report

Indicators to be used (Initial list):

More indicators will be produced during the first two meetings of the project:

• Project Management Level:

- Schedule Performance Index (Budgeted Cost of Work Performed / Budgeted Cost of Work Scheduled)

- Cost Performance Index (Budgeted Cost of Work Performed / Actual Cost of Work Performed)

- Number of meetings carried out (target 5 transnational meetings);

- Number of deliverables submitted on time (target 100%)

- Number of budget revisions (target 0)

- Number of reallocation of responsibilities (target < 10%)

• Project Quality & Impact Level:

- Number of events organised per partner (target 2 local multiplier events)

- Number of trainings provided (target 100%);

- Number of visits of the project website (target >60/ month)

- Number of stakeholders reached (target >100000)

- Number of students trained (target >250);

- Attendance rate at the trainings delivered (target >90%);

• Monitor and Evaluate performance:

- number of participants making use and accessing the Digital Portfolio Portal and the Database of Digital Portfolios  (target >100);

- number of the University services or other institutions promoting and embracing the DPP (target >100);

- number of employers accessing the Database of Digital Portfolios to view student profiles (target >40);

- number of people that attended the 2 local events per country (target > 190);

- suggestions made from members of the target groups participating in the pilot phase for the training course (target < 15);

- of risks with high, medium and low impact which the partners addressed (target <1-2);

- number of risks the partners avoided through the implementation of preventive actions (target =100%);